## Change Log
Project Change Log
Housing Affordability Forecasting System for Greater Darwin
Date | Change made | Reason and action taken | Responsible person | Approved by | Status
2026-08-23 | Updated Jira task allocation and created Sprints 4–6. | Implementation tasks, owners and deadlines were clarified and recorded in Jira. | Lisa Vong | All members | Completed
2026-09-02 | Updated the system architecture. | The original architecture was revised to reflect the actual data sources, processing, modelling and visualisation workflow. | Bipana Tripathee | All members | Completed
2026-09-04 | Prioritised regression and treated affordability classification as a secondary component. | Property price is a continuous target. Linear Regression, Random Forest and XGBoost were selected as the primary models. | Roshan Neupane | All members | Completed
2026-09-07 | Revised the population and income-data approach. | SA2 population data could not be reliably matched with suburb-level property records. More suitable population and temporal variables were selected. | Alan Joshi John | All members | Completed
2026-09-07 | Excluded 2026 property transactions from the current modelling dataset. | Corresponding verified income data was unavailable, so unsupported income values were not estimated. | Alan Joshi John and Roshan Neupane | All members | Completed
2026-09-08 | Tested and updated the data pipeline. | The integrated dataset required validation before final model evaluation. | Alan Joshi John | All members | Completed
2026-09-11 | Re-evaluated model performance after identifying possible data leakage. | Models were rerun using a chronological hold-out test set to improve result reliability. | Roshan Neupane | All members | In Review
2026-09-13 | Updated the risk register and ethics, privacy and security review. | Governance documentation was updated to reflect current implementation risks. Jira tasks PDSPDT-20 and PDSPDT-24 were marked Done. | Aashish Sharma | All members | Completed
2026-09-13 | Updated Jira evidence and verified the Jira link. | Jira records were exported and checked to provide accessible evidence of task allocation and progress. PDSPDT-37 was marked Done. | Lisa Vong | All members | Completed
2026-09-13 | Extended dashboard development and final report integration. | These activities required additional work beyond their original due dates and remain tracked in Jira. | Roshan Neupane and Aashish Sharma | All members | Ongoing